## Total
PROPOSED DEFECT REPORTS - STATUS
NB PDR
| SARPs | Version | CCB Status | Somme
| ADS | IV1.1 | WITHDRAWN | 2
|  |  | ADOPTED | 11
|  | IV2.1 | ADOPTED | 1
|  | IV2.2 | RESOLVED | 8
|  |  | REJECTED | 2
|  |  | WITHDRAWN | 1
|  | IV2.3 | RESOLVED | 9
| Somme ADS |  |  | 34
| CM | IV1.1 | WITHDRAWN | 1
|  |  | ADOPTED | 2
|  | IV2.2 | RESOLVED | 1
|  |  | REJECTED | 1
|  |  | WITHDRAWN | 1
|  | IV2.3 | RESOLVED | 6
| Somme CM |  |  | 12
| CPDLC | IV1.1 | WITHDRAWN | 1
|  |  | ADOPTED | 25
|  | IV2.2 | RESOLVED | 1
|  |  | REJECTED | 2
|  | IV2.3 | RESOLVED | 4
|  |  | WITHDRAWN | 2
| Somme CPDLC |  |  | 35
| FIS | IV1.1 | ADOPTED | 9
|  | IV2.1 | ADOPTED | 2
|  | IV2.2 | RESOLVED | 6
|  |  | REJECTED | 3
|  |  | FORWARDED | 1
|  |  | ADOPTED | 1
|  | IV2.3 | RESOLVED | 9
IV2.3 = Doc 9705 |  |  | REJECTED | 1
| Somme FIS |  |  | 32
| SV2 | IV1.1 | ADOPTED | 2
|  | IV2.2 | ADOPTED | 1
|  | IV2.3 | ACCEPTED | 1
|  |  | RESOLVED | 3
| Somme SV2 |  |  | 7
| Total |  |  | 120

## CCB-Discussion
Ref. | SARPs | Vers. | Title | CCB Status | SME Rec. | Comments | PDR | Impact
97060001 | SV2 | IV1.1 | Errors introduced in version 2.0 | ADOPTED |  | in Doc 9705 | 1
97060002 | CM | IV1.1 | Time Stamp Addition | WITHDRAWN |  |  | 1
97060003 | ADS | IV1.1 | Time Stamp Addition | WITHDRAWN |  |  | 1
97060004 | ADS | IV1.1 | Validity Indication for Downlink Parameters | ADOPTED |  | in Doc 9705 | 1
97060005 | ADS | IV1.1 | Unbounded ASN.1 Types | WITHDRAWN |  |  | 1
97060006 | CPDLC | IV1.1 | Start Collision in CPDLC | ADOPTED |  | in Doc 9705 | 1
97060007 | ADS | IV1.1 | Invalid Reference to 'Flight Id' | ADOPTED |  | in Doc 9705 | 1
97060008 | ADS | IV1.1 | Facility Designation Correction | ADOPTED |  | in Doc 9705 | 1
97060009 | CPDLC | IV1.1 | Facility Designation Correction | ADOPTED |  | in Doc 9705 | 1
97060010 | FIS | IV1.1 | Facility Designation Correction | ADOPTED |  | in Doc 9705 | 1
97060011 | CPDLC | IV1.1 | Revision on Position Definition | ADOPTED |  | in Doc 9705 | 1
97060012 | CPDLC | IV1.1 | Range is Wrong for VHF Frequency Variable | WITHDRAWN |  |  | 1
97060013 | CPDLC | IV1.1 | Missing Uplink Message Element 200 | ADOPTED |  | in Doc 9705 | 1
97080001 | CM | IV1.1 | ETD Correction | ADOPTED |  | in Doc 9705 | 1
97080002 | ADS | IV1.1 | Redundant Reason Code | ADOPTED |  | in Doc 9705 | 1
97080003 | ADS | IV1.1 | Removal of "Speed-units" | ADOPTED |  | in Doc 9705 | 1
97080004 | ADS | IV1.1 | "Shall" in recommendation | ADOPTED |  | in Doc 9705 | 1
97080005 | ADS | IV1.1 | Invalid ASN.1 | ADOPTED |  | in Doc 9705 | 1
97080006 | ADS | IV1.1 | Missing Exception Case | ADOPTED |  | in Doc 9705 | 1
97080007 | ADS | IV1.1 | ATC Connections | ADOPTED |  | in Doc 9705 | 1
97080008 | ADS | IV1.1 | Invalid error handling | ADOPTED |  | in Doc 9705 | 1
97080009 | FIS | IV1.1 | T-LI-1 Timer Expiration | ADOPTED |  | in Doc 9705 | 1
97080010 | CPDLC | IV1.1 | Modification UnitName Definition | ADOPTED |  | in Doc 9705 | 1
97080011 | CPDLC | IV1.1 | Proposed change to ASN.1 UM189 | ADOPTED |  | in Doc 9705 | 1
97080012 | FIS | IV1.1 | ASN.1 Definition of VisibilityNautMiles | ADOPTED |  | in Doc 9705 | 1
97080013 | FIS | IV1.1 | ASN.1 Definition of VerticalVisibility | ADOPTED |  | in Doc 9705 | 1
97100006 | CM | IV1.1 | Exception Handling Correction | ADOPTED |  | in Doc 9705 | 1
97100007 | ADS | IV1.1 | Reception of a negative D-START confirmation | ADOPTED |  | in Doc 9705 | 1
97100008 | CPDLC | IV1.1 | Position Report Format Change in PANSRAC | ADOPTED |  | in Doc 9705 | 1
97100009 | CPDLC | IV1.1 | Not permitted PDU in D-END indication | ADOPTED |  | in Doc 9705 | 1
97100010 | CPDLC | IV1.1 | Incorrect range for LevelFeet parameter | ADOPTED |  | in Doc 9705 | 1
97100011 | CPDLC | IV1.1 | Reduction on Potential Message Size | ADOPTED |  | in Doc 9705 | 1
97100012 | CPDLC | IV1.1 | Invalid Message Response | ADOPTED |  | in Doc 9705 | 1
97100013 | CPDLC | IV1.1 | Additional Traffic Type | ADOPTED |  | in Doc 9705 | 1
97100014 | CPDLC | IV1.1 | Routing Class must be ATC | ADOPTED |  | in Doc 9705 | 1
97100015 | CPDLC | IV1.1 | Airway name changed to ATSRouteDesignator | ADOPTED |  | in Doc 9705 | 1
97100016 | CPDLC | IV1.1 | VHF Frequency/Frequencyvhfchannel | ADOPTED |  | in Doc 9705 | 1
97100017 | CPDLC | IV1.1 | Unrecoverable Error only as recommendation | ADOPTED |  | in Doc 9705 | 1
97100018 | CPDLC | IV1.1 | Additional data in the ERROR message | ADOPTED |  | in Doc 9705 | 1
97100019 | CPDLC | IV1.1 | Facility Function ASN.1 definition | ADOPTED |  | in Doc 9705 | 1
97100020 | FIS | IV1.1 | Invalid parameter description of the FIS-Update-Contract response | ADOPTED |  | in Doc 9705 | 1
97100021 | FIS | IV1.1 | ArrivalRunway ASN.1 Definition | ADOPTED |  | in Doc 9705 | 1
97100022 | FIS | IV1.1 | Maximum Size of an ATIS Report | ADOPTED |  | in Doc 9705 | 1
97100023 | FIS | IV1.1 | Positive Ack on a negative contract-update response | ADOPTED |  | in Doc 9705 | 1
97100025 | CPDLC | IV1.1 | Meaningless Requirement Can Not Be Met | ADOPTED |  | in Doc 9705 | 1
97100026 | CPDLC | IV1.1 | Exception Handling Correction | ADOPTED |  | in Doc 9705 | 1
97100029 | SV2 | IV1.1 | Various editorial defects | ADOPTED |  | in Doc 9705 | 1
97100034 | FIS | IV1.1 | Reception of a Cancel Contracts Accept APDU | ADOPTED |  | in Doc 9705 | 1
97100036 | CPDLC | IV1.1 | Distance Offset Definition | ADOPTED |  | in Doc 9705 | 1
97100037 | CPDLC | IV1.1 | Reserved Message Element | ADOPTED |  | in Doc 9705 | 1
97100038 | CPDLC | IV1.1 | MAYDAY / PAN PAN PAN | ADOPTED |  | in Doc 9705 | 1
97100039 | CPDLC | IV1.1 | CPDLC Route Clearance | ADOPTED |  | in Doc 9705 | 1
97110003 | FIS | IV2.1 | Update Contract cancelled during contract establshment | ADOPTED |  | in Doc 9705 | 1
97110004 | FIS | IV2.1 | Invalid values for t-DC-2 and t-UC-2 | ADOPTED |  | in Doc 9705 | 1
97120002 | ADS | IV2.1 | Validity Indication for Downlink Parameters | ADOPTED |  | in Doc 9705 | 1
98030001 | ADS | IV2.2 | Error in tables 2.2.1.5-31 and 32 | RESOLVED |  | in Doc 9705 | 1 | C
98030004 | ADS | IV2.2 | Editorial Errors | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98030006 | FIS | IV2.2 | Alignment of the ASN.1 description | ADOPTED |  | in Doc 9705 | 1
98040001 | FIS | IV2.2 | Simultaneous air and ground cancellation | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98040002 | FIS | IV2.2 | FIS-provider-abort Reason parameter | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98040004 | CPDLC | IV1.1 | Comparison of Doc 9795 with Doc 4444 | ADOPTED |  | in Doc 9705 | 1
98040005 | SV2 | IV2.2 | ICAO Edition 2.2 Editorials | ADOPTED |  | in Doc 9705 | 1
98040006 | FIS | IV2.2 | t-inactivity timer management | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98040007 | FIS | IV2.2 | Invalid list of allowed APDUs in D-START cnf | FORWARDED |  |  | 1 | n/a
98040008 | FIS | IV2.2 | Invalid state change | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98050002 | CM | IV2.2 | Incomplete requirement | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98050003 | CM | IV2.2 | Erroneous handling of unexpected QOS | REJECTED |  |  | 1 | n/a
98050004 | ADS | IV2.2 | Minor defects | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98050005 | ADS | IV2.2 | Useless parameters passed from PC to LI | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98050006 | ADS | IV2.2 | Erroneous parameter name and PDU element name for cancel event contract | REJECTED |  |  | 1 | n/a
98050007 | ADS | IV2.2 | Erroneous exception handling for D-START confirmation | REJECTED |  |  | 1 | n/a
98050008 | ADS | IV2.2 | Erroneous exception handling for D-DATA indication | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98050009 | ADS | IV2.2 | Erroneous exception handling for D-ABORT indication | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98050010 | ADS | IV2.2 | Erroneous exception handling for D-END confirmation | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98050011 | CPDLC | IV2.2 | Incomplete requirement | REJECTED |  |  | 1 | n/a
98050012 | CPDLC | IV2.2 | Erroneous handling of unexpected QOS | REJECTED |  |  | 1 | n/a
98050013 | FIS | IV2.2 | Minor defects | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98050014 | FIS | IV2.2 | Inspecified initial state in transitions | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98050015 | FIS | IV2.2 | Error in Altimeter setting | REJECTED |  |  | 1 | n/a
98050016 | FIS | IV2.2 | Extraneous transitions in ground LI and air LI modules | REJECTED |  |  | 1 | n/a
98050017 | FIS | IV2.2 | Additional APDU to expect in D-START confirmation | REJECTED |  |  | 1 | n/a
98050018 | ADS | IV2.2 | State table/Protocol Description inconsistency | WITHDRAWN |  |  | 1 | n/a
98050019 | CPDLC | IV2.2 | Problems with ICAO V2.2 CPDLC SARPs | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98050020 | CM | IV2.2 | CMLogonResponse Correction | WITHDRAWN |  |  | 1 | n/a
98060001 | ADS | IV2.2 | EPP Issue | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98070001 | CM | IV2.3 | Timer Activation | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98070002 | ADS | IV2.3 | Error in the ARF protocol | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98070003 | SV2 | IV2.3 | Engineering Version Discrepancies and Editorial Errors | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98090001 | ADS | IV2.3 | ASN.1 syntax error | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98090005 | CM | IV2.3 | Facility Designation User Requirements Correction | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98090008 | FIS | IV2.3 | ASN.1 Syntax Error | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98100001 | CPDLC | IV2.3 | CPDLC vs. ICAO Doc 4444, Amd 2 | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98100008 | ADS | IV2.3 | State table/Protocol Description inconsistency (2nd Issue) | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98110002 | SV2 | IV2.3 | Exception Handling Situation missing | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98110003 | FIS | IV2.3 | Stop t-LI-1 Timer | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98110004 | FIS | IV2.3 | D-END allowed only if no contract in place | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120001 | ADS | IV2.3 | PDR 97100007 Follow-up | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120002 | ADS | IV2.3 | LI Problems Abort Situations | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98120003 | ADS | IV2.3 | D-START QOS Routing Class | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120004 | ADS | IV2.3 | D-START Calling Peer Id | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120005 | CM | IV2.3 | Timers need to be reset | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98120006 | CM | IV2.3 | QOS in D-START primitives | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120007 | CM | IV2.3 | D-START Calling Peer Id | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120008 | CM | IV2.3 | Conflicting requirements | RESOLVED |  | in Doc 9705/Amd 1 | 1 | D
98120009 | CPDLC | IV2.3 | QOS routing class in D-START primitives | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98120010 | CPDLC | IV2.3 | D-START Calling Peer Id | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120011 | FIS | IV2.3 | Actions upon t-LI timer expiration | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120012 | FIS | IV2.3 | FIS Abort Codes ASN.1 | REJECTED |  |  | 1 | n/a
98120013 | FIS | IV2.3 | LI Abort Situations | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120014 | FIS | IV2.3 | QOS in D-START primitives | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
98120015 | ADS | IV2.3 | Invalid Value for the Originator parameter | RESOLVED |  | in Doc 9705/Amd 1 | 1 | B
98120016 | FIS | IV2.3 | Error in Subsetting Rules | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
99010003 | CPDLC | IV2.3 | Closure Messages | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
99010004 | SV2 | IV2.3 | Editorial Errors | ACCEPTED |  |  | 1
99010006 | FIS | IV2.3 | D-START Calling Peer Id | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
99030003 | ADS | IV2.3 | QOS in D-START primitives (ARF) | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C
99040001 | FIS | IV2.3 | Invalid default value for the ATIS type | RESOLVED |  | in Doc 9705/Amd 1 | 1 | A
99040004 | CPDLC | IV2.3 | 8.33 spacing | WITHDRAWN |  |  | 1 | ?
99040005 | CPDLC | IV2.3 | Error message with concatenated free text | WITHDRAWN |  |  | 1 | n/a
99050003 | SV2 | IV2.3 | New chapter 8 | RESOLVED |  | in Doc 9705/Amd 1 | 1 | C